## v5.05.23
Project Description: | 2025 South Beach E-H Renovation | [7 empty] | REV #:
Contract Date: | 2024-10-15 | [7 empty] | REV DATE:
Job#: | 24-835
Revenue - Product | 132474
Revenue - Measure | 5300
Revenue - InstaII | 61150
Revenue - Freight
198924
*** Notate if RWP Labor or SubContracted
FABRICATION | ORIGINAL BUDGET |  |  | REVISIONS |  | CURRENT BUDGET |  |  | NOTES
Labor - Ripplefold Drapery *** | 01-010 L S | 25588.8 | 0% | 0 | 0% | 25588.8 | 12.86% | *** | 360 RF
Labor - Ripplefold Sheer *** | 01-020 L S | 17575.2 | 0% | 0 | 0% | 17575.2 | 8.835% | *** | 1680 Widths
Labor - Pinch Pleat Drapery *** | 01-030 L S | 0 | 0% | 0 | 0% | 0 | 0% | *** | 4957 Yards
Labor - Pinch Pleat Sheer *** | 01-040 L S | 0 | 0% | 0 | 0% | 0 | 0% | *** | 360 RF Sheer
Labor - Cubicle Curtain Labor *** | 01-070 L S | 0 | 0% | 0 | 0% | 0 | 0% | *** | 1440 Widths
Labor - Valances *** | 03-020 L S | 0 | 0% | 0 | 0% | 0 | 0% | *** | 2536 Yards
Labor - Cornices *** | 03-010 L S | 0 | 0% | 0 | 0% | 0 | 0% | ***
Labor - Roman Shades *** | 01-080 L S | 13327.38 | 0% | 0 | 0% | 13327.38 | 6.7% | *** | 117 Flat Romans
Labor - RWP Roller Shades | 05-035 L | 36 | 0% | 0 | 0% | 36 | 0.0181% |  | 3 Motorized Singles
Material - Hardware - Drapery (ALL) | 02-040 M | 29895 | 0% | 0 | 0% | 29895 | 15.03%
Material - Fabric (CULP) | 01-050 M | 0 | 0% | 0 | 0% | 0 | 0%
Material - Fabric (BUY-IN) | 01-050 BI | 0 | 0% | 0 | 0% | 0 | 0%
Material - Lining (ALL) | 01-060 M | 11146.01 | 0% | 0 | 0% | 11146.01 | 5.603% |  | 3160 Yards
Material - Roman Shades (RWP FAB) | 01-080 M | 2925 | 0% | 0 | 0% | 2925 | 1.47%
Material - Roman Shades (BUY-IN SHADES) | 01-080 BI | 0 | 0% | 0 | 0% | 0 | 0%
Material - Roller Shades (BUY-IN SHADES) | 05-030 BI | 0 | 0% | 0 | 0% | 0 | 0%
Material - Roller Shades (RWP FAB) | 05-035 M | 789.99 | 0% | 0 | 0% | 789.99 | 0.3971% |  | Solatech 404377
Material - Shutters (BUY-IN) | 06-020 BI | 0 | 0% | 0 | 0% | 0 | 0%
Material - Blinds (BUY-IN) | 04-020 BI | 0 | 0% | 0 | 0% | 0 | 0%
Labor - Soft Goods - Bed Skirts | 10-010 S | 0 | 0% | 0 | 0% | 0 | 0%
Labor - Soft Goods - Boxspring Cvr | 10-020 S | 0 | 0% | 0 | 0% | 0 | 0%
Labor - Soft Goods - Bedscarves | 10-030 S | 0 | 0% | 0 | 0% | 0 | 0%
Labor - Soft Goods - Pillows | 10-050 S | 0 | 0% | 0 | 0% | 0 | 0%
Labor - Soft Goods - Shower Curtains | 10-070 S | 0 | 0% | 0 | 0% | 0 | 0%
Labor - Soft Goods - Bed Bases *** | 10-080 L S | 0 | 0% | 0 | 0% | 0 | 0% | ***
Material - Soft Goods Fabric (CULP) | 10-040 M | 0 | 0% | 0 | 0% | 0 | 0%
Material - Soft Goods Fabric (BUY-IN) | 10-040 BI | 0 | 0% | 0 | 0% | 0 | 0%
Material - Soft Goods Lining (ALL) | 10-060 M | 0 | 0% | 0 | 0% | 0 | 0%
Material - Soft Goods Bed Bases | 10-080 M | 0 | 0% | 0 | 0% | 0 | 0%
|  | 101283.38 | 0% | 0 | 0% | 101283.38 | 50.92%
SERVICES | ORIGINAL BUDGET |  |  | REVISIONS |  | CURRENT BUDGET |  |  | NOTES
Measure - Contract Services (Incl All Expenses Paid to Sub) | 09-010 S | 0 | 0% | 0 | 0% | 0 | 0%
Measure - RWP Labor Hours | 09-010 L | 1750 | 0% | 0 | 0% | 1750 | 0.8797%
Measure - RWP Travel Expenses | 09-010 T | 1521 |  | 0 |  | 1521
Contract Labor - Installation (Incl All Expenses Paid to Sub) | 09-055 S | 0 | 0% | 0 | 0% | 0 | 0%
Installation - RWP Labor Hours | 09-055 L | 36375 | 0% | 0 | 0% | 36375 | 18.29%
Installation - RWP Travel | 09-055 T | 14976 | 0% | 0 |  | 14976
Installation - RWP Misc Supplies | 09-055 M | 0 | 0% | 0 |  | 0
Freight - Non-BiIIabIe (INCLD IN PRODUCT SALE) | 09-070 F | 0 | 0% | 0 | 0% | 0 | 0%
Freight - BiIIabIe | 09-080 F | 0 | 0% | 0 | 0% | 0 | 0%
Storage (INCL IN SALES EST) | 09-055 R | 0 | 0% | 0 | 0% | 0 | 0% |  | CommissionabIe SaIes | 121327.99
|  | 54622 | 0% | 0 | 0% | 54622 | 19.17% |  | SaIes Rep(s) | 6% | TotaI
[9 empty] | Gorab | 6% | 7279.6794
| TOTAL COGS | 155905.38 | 0.78374 | 0 | 0% | 155905.38 | 78.37% |  |  | 0% | 0
| NET PROFIT | 43018.62 | 0.21626 | 0 | 0% | 43018.62 | 21.63% |  | Non-CuIp Buy-In Fabric Reduced From CommissionabIe SaIes
[9 empty] | Buy-In Fabric: | 0
[9 empty] | Lining Fabric: | 11146.01