## v5.05.23
Project Description: | Patriots Place - Phase 2 - 2025 | [7 empty] | REV #:
Contract Date: | 2025-02-13 | [7 empty] | REV DATE:
Job#: | 25-161
Revenue - Product | 136263.75
Revenue - Measure | 9900
Revenue - InstaII | 67600
Revenue - Freight
213763.75
*** Notate if RWP Labor or SubContracted
FABRICATION | ORIGINAL BUDGET |  |  | REVISIONS |  | CURRENT BUDGET |  |  | NOTES
Labor - Ripplefold Drapery *** | 01-010 L S | 25008.96 | 0% | 0 | 0% | 25008.96 | 11.7% | *** | 504 RF
Labor - Ripplefold Sheer *** | 01-020 L S | 22062.96 | 0% | 0 | 0% | 22062.96 | 10.32% | *** | 1912 Widths
Labor - Pinch Pleat Drapery *** | 01-030 L S | 0 | 0% | 0 | 0% | 0 | 0% | *** | 1908 Yards
Labor - Pinch Pleat Sheer *** | 01-040 L S | 0 | 0% | 0 | 0% | 0 | 0% | *** | 504 RF Sheer
Labor - Cubicle Curtain Labor *** | 01-070 L S | 0 | 0% | 0 | 0% | 0 | 0% | *** | 1912 Widths
Labor - Valances *** | 03-020 L S | 10205.65 | 0% | 0 | 0% | 10205.65 | 4.774% | *** | 1878 Yards
Labor - Cornices *** | 03-010 L S | 0 | 0% | 0 | 0% | 0 | 0% | *** | 204 - Scalloped Valances/667 Yards
Labor - Roman Shades *** | 01-080 L S | 2997.12 | 0% | 0 | 0% | 2997.12 | 1.402% | *** | 16 - Hobbled Romans
Labor - RWP Roller Shades | 05-035 L | 192 | 0% | 0 | 0% | 192 | 0.08982% |  | 16 - Manual Singles
Material - Hardware - Drapery (ALL) | 02-040 M | 34267 | 0% | 0 | 0% | 34267 | 16.03% |  | CTM
Material - Fabric (CULP) | 01-050 M | 0 | 0% | 0 | 0% | 0 | 0%
Material - Fabric (BUY-IN) | 01-050 BI | 0 | 0% | 0 | 0% | 0 | 0%
Material - Lining (ALL) | 01-060 M | 2034.35 | 0% | 0 | 0% | 2034.35 | 0.9517% |  | 667 Yards (Valances)
Material - Roman Shades (RWP FAB) | 01-080 M | 400 | 0% | 0 | 0% | 400 | 0.1871%
Material - Roman Shades (BUY-IN SHADES) | 01-080 BI | 0 | 0% | 0 | 0% | 0 | 0%
Material - Roller Shades (BUY-IN SHADES) | 05-030 BI | 0 | 0% | 0 | 0% | 0 | 0%
Material - Roller Shades (RWP FAB) | 05-035 M | 684.8 | 0% | 0 | 0% | 684.8 | 0.3204% |  | Solatech 429443
Material - Shutters (BUY-IN) | 06-020 BI | 0 | 0% | 0 | 0% | 0 | 0%
Material - Blinds (BUY-IN) | 04-020 BI | 1386 | 0% | 0 | 0% | 1386 | 0.6484% |  | 21 - Caco 2" Faux Wood
Labor - Soft Goods - Bed Skirts | 10-010 S | 0 | 0% | 0 | 0% | 0 | 0% |  |  | COM: Panaz Grandeur Custom Indigo
Labor - Soft Goods - Boxspring Cvr | 10-020 S | 0 | 0% | 0 | 0% | 0 | 0% |  | COM: Panaz Grandeur Custom Ombre Indigo
Labor - Soft Goods - Bedscarves | 10-030 S | 0 | 0% | 0 | 0% | 0 | 0% |  |  | COM: P Kaufmann Fair Lead Sheer Paraffin
Labor - Soft Goods - Pillows | 10-050 S | 0 | 0% | 0 | 0% | 0 | 0%
Labor - Soft Goods - Shower Curtains | 10-070 S | 0 | 0% | 0 | 0% | 0 | 0%
Labor - Soft Goods - Bed Bases *** | 10-080 L S | 0 | 0% | 0 | 0% | 0 | 0% | ***
Material - Soft Goods Fabric (CULP) | 10-040 M | 0 | 0% | 0 | 0% | 0 | 0%
Material - Soft Goods Fabric (BUY-IN) | 10-040 BI | 0 | 0% | 0 | 0% | 0 | 0%
Material - Soft Goods Lining (ALL) | 10-060 M | 0 | 0% | 0 | 0% | 0 | 0%
Material - Soft Goods Bed Bases | 10-080 M | 0 | 0% | 0 | 0% | 0 | 0%
|  | 99238.84 | 0% | 0 | 0% | 99238.84 | 46.42%
SERVICES | ORIGINAL BUDGET |  |  | REVISIONS |  | CURRENT BUDGET |  |  | NOTES
Measure - Contract Services (Incl All Expenses Paid to Sub) | 09-010 S | 0 | 0% | 0 | 0% | 0 | 0%
Measure - RWP Labor Hours | 09-010 L | 2800 | 0% | 0 | 0% | 2800 | 1.31%
Measure - RWP Travel Expenses | 09-010 T | 3890 |  | 0 |  | 3890
Contract Labor - Installation (Incl All Expenses Paid to Sub) | 09-055 S | 0 | 0% | 0 | 0% | 0 | 0%
Installation - RWP Labor Hours | 09-055 L | 31235 | 0% | 0 | 0% | 31235 | 14.61%
Installation - RWP Travel | 09-055 T | 25520 | 0% | 0 |  | 25520
Installation - RWP Misc Supplies | 09-055 M | 0 | 0% | 0 |  | 0
Freight - Non-BiIIabIe (INCLD IN PRODUCT SALE) | 09-070 F | 0 | 0% | 0 | 0% | 0 | 0%
Freight - BiIIabIe | 09-080 F | 0 | 0% | 0 | 0% | 0 | 0%
Storage (INCL IN SALES EST) | 09-055 R | 0 | 0% | 0 | 0% | 0 | 0% |  | CommissionabIe SaIes | 134229.4
|  | 63445 | 0% | 0 | 0% | 63445 | 15.92% |  | SaIes Rep(s) | 6% | TotaI
[9 empty] | Gorab | 6% | 8053.764
| TOTAL COGS | 162683.84 | 0.76105 | 0 | 0% | 162683.84 | 76.1% |  |  | 0% | 0
| NET PROFIT | 51079.91 | 0.23895 | 0 | 0% | 51079.91 | 23.9% |  | Non-CuIp Buy-In Fabric Reduced From CommissionabIe SaIes
[9 empty] | Buy-In Fabric: | 0
[9 empty] | Lining Fabric: | 2034.35