## v5.05.23
Project Description: | 2024 South Beach C&D Renovation Phase 1 | [7 empty] | REV #:
Contract Date: | 2024-07-29 | [7 empty] | REV DATE:
Job#: | 24-194
Revenue - Product | 67490.5
Revenue - Measure | 3800
Revenue - InstaII | 32050
Revenue - Freight
103340.5
*** Notate if RWP Labor or SubContracted
FABRICATION | ORIGINAL BUDGET |  |  | REVISIONS |  | CURRENT BUDGET |  |  | NOTES
Labor - Ripplefold Drapery *** | 01-010 L S | 12544.8 | 0% | 0 | 0% | 12544.8 | 12.14% | *** | 180 RF
Labor - Ripplefold Sheer *** | 01-020 L S | 8877.6 | 0% | 0 | 0% | 8877.6 | 8.591% | *** | 810 Widths
Labor - Pinch Pleat Drapery *** | 01-030 L S | 0 | 0% | 0 | 0% | 0 | 0% | *** | 2293 Yards
Labor - Pinch Pleat Sheer *** | 01-040 L S | 0 | 0% | 0 | 0% | 0 | 0% | *** | 180 RF Sheer
Labor - Cubicle Curtain Labor *** | 01-070 L S | 0 | 0% | 0 | 0% | 0 | 0% | *** | 720 Widths
Labor - Valances *** | 03-020 L S | 0 | 0% | 0 | 0% | 0 | 0% | *** | 1402 Yards
Labor - Cornices *** | 03-010 L S | 0 | 0% | 0 | 0% | 0 | 0% | ***
Labor - Roman Shades *** | 01-080 L S | 6436.32 | 0% | 0 | 0% | 6436.32 | 6.228% | *** | 56 Flat Romans
Labor - RWP Roller Shades | 05-035 L | 48 | 0% | 0 | 0% | 48 | 0.04645% |  | 4 Motorized Singles
Material - Hardware - Drapery (ALL) | 02-040 M | 14933 | 0% | 0 | 0% | 14933 | 14.45% |  | CTM
Material - Fabric (CULP) | 01-050 M | 0 | 0% | 0 | 0% | 0 | 0%
Material - Fabric (BUY-IN) | 01-050 BI | 0 | 0% | 0 | 0% | 0 | 0%
Material - Lining (ALL) | 01-060 M | 6282.85 | 0% | 0 | 0% | 6282.85 | 6.08% |  | 2220 Yards
Material - Roman Shades (RWP FAB) | 01-080 M | 1400 | 0% | 0 | 0% | 1400 | 1.355%
Material - Roman Shades (BUY-IN SHADES) | 01-080 BI | 0 | 0% | 0 | 0% | 0 | 0%
Material - Roller Shades (BUY-IN SHADES) | 05-030 BI | 0 | 0% | 0 | 0% | 0 | 0%
Material - Roller Shades (RWP FAB) | 05-035 M | 1026.88 | 0% | 0 | 0% | 1026.88 | 0.9937% |  | Solatech 387531
Material - Shutters (BUY-IN) | 06-020 BI | 0 | 0% | 0 | 0% | 0 | 0%
Material - Blinds (BUY-IN) | 04-020 BI | 0 | 0% | 0 | 0% | 0 | 0%
Labor - Soft Goods - Bed Skirts | 10-010 S | 0 | 0% | 0 | 0% | 0 | 0%
Labor - Soft Goods - Boxspring Cvr | 10-020 S | 0 | 0% | 0 | 0% | 0 | 0%
Labor - Soft Goods - Bedscarves | 10-030 S | 0 | 0% | 0 | 0% | 0 | 0%
Labor - Soft Goods - Pillows | 10-050 S | 0 | 0% | 0 | 0% | 0 | 0%
Labor - Soft Goods - Shower Curtains | 10-070 S | 0 | 0% | 0 | 0% | 0 | 0%
Labor - Soft Goods - Bed Bases *** | 10-080 L S | 0 | 0% | 0 | 0% | 0 | 0% | ***
Material - Soft Goods Fabric (CULP) | 10-040 M | 0 | 0% | 0 | 0% | 0 | 0%
Material - Soft Goods Fabric (BUY-IN) | 10-040 BI | 0 | 0% | 0 | 0% | 0 | 0%
Material - Soft Goods Lining (ALL) | 10-060 M | 0 | 0% | 0 | 0% | 0 | 0%
Material - Soft Goods Bed Bases | 10-080 M | 0 | 0% | 0 | 0% | 0 | 0%
|  | 51549.45 | 0% | 0 | 0% | 51549.45 | 49.88%
SERVICES | ORIGINAL BUDGET |  |  | REVISIONS |  | CURRENT BUDGET |  |  | NOTES
Measure - Contract Services (Incl All Expenses Paid to Sub) | 09-010 S | 0 | 0% | 0 | 0% | 0 | 0%
Measure - RWP Labor Hours | 09-010 L | 1050 | 0% | 0 | 0% | 1050 | 1.016%
Measure - RWP Travel Expenses | 09-010 T | 1521 |  | 0 |  | 1521
Contract Labor - Installation (Incl All Expenses Paid to Sub) | 09-055 S | 0 | 0% | 0 | 0% | 0 | 0%
Installation - RWP Labor Hours | 09-055 L | 18250 | 0% | 0 | 0% | 18250 | 17.66%
Installation - RWP Travel | 09-055 T | 8784 | 0% | 0 |  | 8784
Installation - RWP Misc Supplies | 09-055 M | 0 | 0% | 0 |  | 0
Freight - Non-BiIIabIe (INCLD IN PRODUCT SALE) | 09-070 F | 0 | 0% | 0 | 0% | 0 | 0%
Freight - BiIIabIe | 09-080 F | 0 | 0% | 0 | 0% | 0 | 0%
Storage (INCL IN SALES EST) | 09-055 R | 0 | 0% | 0 | 0% | 0 | 0% |  | CommissionabIe SaIes | 61207.65
|  | 29605 | 0% | 0 | 0% | 29605 | 18.68% |  | SaIes Rep(s) | 6% | TotaI
[9 empty] | Gorab | 6% | 3672.459
| TOTAL COGS | 81154.45 | 0.78531 | 0 | 0% | 81154.45 | 78.53% |  |  | 0% | 0
| NET PROFIT | 22186.05 | 0.21469 | 0 | 0% | 22186.05 | 21.47% |  | Non-CuIp Buy-In Fabric Reduced From CommissionabIe SaIes
[9 empty] | Buy-In Fabric: | 0
[9 empty] | Lining Fabric: | 6282.85