## v5.05.23
Project Description: | 2024 Condo IV River Island (Phase 1) | [7 empty] | REV #:
Contract Date: | 2024-10-05 | [7 empty] | REV DATE:
Job#: | 24-147
Revenue - Product | 30396
Revenue - Measure | 900
Revenue - InstaII | 10125
Revenue - Freight | 900
42321
*** Notate if RWP Labor or SubContracted
FABRICATION | ORIGINAL BUDGET |  |  | REVISIONS |  | CURRENT BUDGET |  |  | NOTES
Labor - Ripplefold Drapery *** | 01-010 L S | 0 | 0% | 0 | 0% | 0 | 0% | ***
Labor - Ripplefold Sheer *** | 01-020 L S | 0 | 0% | 0 | 0% | 0 | 0% | ***
Labor - Pinch Pleat Drapery *** | 01-030 L S | 0 | 0% | 0 | 0% | 0 | 0% | ***
Labor - Pinch Pleat Sheer *** | 01-040 L S | 0 | 0% | 0 | 0% | 0 | 0% | ***
Labor - Cubicle Curtain Labor *** | 01-070 L S | 0 | 0% | 0 | 0% | 0 | 0% | ***
Labor - Valances *** | 03-020 L S | 0 | 0% | 0 | 0% | 0 | 0% | ***
Labor - Cornices *** | 03-010 L S | 0 | 0% | 0 | 0% | 0 | 0% | ***
Labor - Roman Shades *** | 01-080 L S | 0 | 0% | 0 | 0% | 0 | 0% | ***
Labor - RWP Roller Shades | 05-035 L | 1824 | 0% | 0 | 0% | 1824 | 4.31% |  | 76 Manual Duals
Material - Hardware - Drapery (ALL) | 02-040 M | 0 | 0% | 0 | 0% | 0 | 0%
Material - Fabric (CULP) | 01-050 M | 0 | 0% | 0 | 0% | 0 | 0%
Material - Fabric (BUY-IN) | 01-050 BI | 0 | 0% | 0 | 0% | 0 | 0%
Material - Lining (ALL) | 01-060 M | 0 | 0% | 0 | 0% | 0 | 0%
Material - Roman Shades (RWP FAB) | 01-080 M | 0 | 0% | 0 | 0% | 0 | 0%
Material - Roman Shades (BUY-IN SHADES) | 01-080 BI | 0 | 0% | 0 | 0% | 0 | 0%
Material - Roller Shades (BUY-IN SHADES) | 05-030 BI | 0 | 0% | 0 | 0% | 0 | 0%
Material - Roller Shades (RWP FAB) | 05-035 M | 23094.72 | 0% | 0 | 0% | 23094.72 | 54.57% |  | Solatech 302357
Material - Shutters (BUY-IN) | 06-020 BI | 0 | 0% | 0 | 0% | 0 | 0%
Material - Blinds (BUY-IN) | 04-020 BI | 0 | 0% | 0 | 0% | 0 | 0%
Labor - Soft Goods - Bed Skirts | 10-010 S | 0 | 0% | 0 | 0% | 0 | 0%
Labor - Soft Goods - Boxspring Cvr | 10-020 S | 0 | 0% | 0 | 0% | 0 | 0%
Labor - Soft Goods - Bedscarves | 10-030 S | 0 | 0% | 0 | 0% | 0 | 0%
Labor - Soft Goods - Pillows | 10-050 S | 0 | 0% | 0 | 0% | 0 | 0%
Labor - Soft Goods - Shower Curtains | 10-070 S | 0 | 0% | 0 | 0% | 0 | 0%
Labor - Soft Goods - Bed Bases *** | 10-080 L S | 0 | 0% | 0 | 0% | 0 | 0% | ***
Material - Soft Goods Fabric (CULP) | 10-040 M | 0 | 0% | 0 | 0% | 0 | 0%
Material - Soft Goods Fabric (BUY-IN) | 10-040 BI | 0 | 0% | 0 | 0% | 0 | 0%
Material - Soft Goods Lining (ALL) | 10-060 M | 0 | 0% | 0 | 0% | 0 | 0%
Material - Soft Goods Bed Bases | 10-080 M | 0 | 0% | 0 | 0% | 0 | 0%
|  | 24918.72 | 0% | 0 | 0% | 24918.72 | 58.88%
SERVICES | ORIGINAL BUDGET |  |  | REVISIONS |  | CURRENT BUDGET |  |  | NOTES
Measure - Contract Services (Incl All Expenses Paid to Sub) | 09-010 S | 0 | 0% | 0 | 0% | 0 | 0%
Measure - RWP Labor Hours | 09-010 L | 350 | 0% | 0 | 0% | 350 | 0.827%
Measure - RWP Travel Expenses | 09-010 T | 125 |  | 0 |  | 125
Contract Labor - Installation (Incl All Expenses Paid to Sub) | 09-055 S | 0 | 0% | 0 | 0% | 0 | 0%
Installation - RWP Labor Hours | 09-055 L | 6080 | 0% | 0 | 0% | 6080 | 14.37%
Installation - RWP Travel | 09-055 T | 125 | 0% | 0 |  | 125
Installation - RWP Misc Supplies | 09-055 M | 0 | 0% | 0 |  | 0
Freight - Non-BiIIabIe (INCLD IN PRODUCT SALE) | 09-070 F | 0 | 0% | 0 | 0% | 0 | 0%
Freight - BiIIabIe | 09-080 F | 0 | 0% | 0 | 0% | 0 | 0%
Storage (INCL IN SALES EST) | 09-055 R | 0 | 0% | 0 | 0% | 0 | 0% |  | CommissionabIe SaIes | 30396
|  | 6680 | 0% | 0 | 0% | 6680 | 15.19% |  | SaIes Rep(s) | 6% | TotaI
[9 empty] | Gorab | 6% | 1823.76
| TOTAL COGS | 31598.72 | 0.74664 | 0 | 0% | 31598.72 | 74.66% |  |  | 0% | 0
| NET PROFIT | 10722.28 | 0.25336 | 0 | 0% | 10722.28 | 25.34% |  | Non-CuIp Buy-In Fabric Reduced From CommissionabIe SaIes
[9 empty] | Buy-In Fabric: | 0
[9 empty] | Lining Fabric: | 0