## v5.05.23
Project Description: | Doubletree - Lawrenceburg, IN | [7 empty] | REV #: | 4
Contract Date: | 2025-02-07 | [7 empty] | REV DATE: | 2025-06-24
Job#: | 25-142
Revenue - Product | 120237.95
Revenue - Measure
Revenue - InstaII
Revenue - Freight
120237.95
*** Notate if RWP Labor or SubContracted
FABRICATION | ORIGINAL BUDGET |  |  | REVISIONS |  | CURRENT BUDGET |  |  | NOTES
Labor - Ripplefold Drapery *** | 01-010 L S | 0 | 0% | 0 | 0% | 0 | 0% | ***
Labor - Ripplefold Sheer *** | 01-020 L S | 0 | 0% | 0 | 0% | 0 | 0% | ***
Labor - Pinch Pleat Drapery *** | 01-030 L S | 0 | 0% | 0 | 0% | 0 | 0% | ***
Labor - Pinch Pleat Sheer *** | 01-040 L S | 0 | 0% | 0 | 0% | 0 | 0% | ***
Labor - Cubicle Curtain Labor *** | 01-070 L S | 0 | 0% | 0 | 0% | 0 | 0% | ***
Labor - Valances *** | 03-020 L S | 0 | 0% | 0 | 0% | 0 | 0% | ***
Labor - Cornices *** | 03-010 L S | 0 | 0% | 0 | 0% | 0 | 0% | ***
Labor - Roman Shades *** | 01-080 L S | 0 | 0% | 0 | 0% | 0 | 0% | ***
Labor - RWP Roller Shades | 05-035 L | 4248 | 0% | 384 | 0.3194% | 4632 | 3.852% |  | 170 Manual Duals,15 Motorized Duals,6 Manual Singles
Material - Hardware - Drapery (ALL) | 02-040 M | 0 | 0% | 0 | 0% | 0 | 0%
Material - Fabric (CULP) | 01-050 M | 0 | 0% | 0 | 0% | 0 | 0%
Material - Fabric (BUY-IN) | 01-050 BI | 0 | 0% | 0 | 0% | 0 | 0%
Material - Lining (ALL) | 01-060 M | 0 | 0% | 0 | 0% | 0 | 0%
Material - Roman Shades (RWP FAB) | 01-080 M | 0 | 0% | 0 | 0% | 0 | 0%
Material - Roman Shades (BUY-IN SHADES) | 01-080 BI | 0 | 0% | 0 | 0% | 0 | 0%
Material - Roller Shades (BUY-IN SHADES) | 05-030 BI | 0 | 0% | 0 | 0% | 0 | 0%
Material - Roller Shades (RWP FAB) | 05-035 M | 85309.89 | 0% | 4717.63 | 3.924% | 90027.52 | 74.87% |  | RWP1676 [R-481]
Material - Shutters (BUY-IN) | 06-020 BI | 0 | 0% | 0 | 0% | 0 | 0%
Material - Blinds (BUY-IN) | 04-020 BI | 0 | 0% | 0 | 0% | 0 | 0%
Labor - Soft Goods - Bed Skirts | 10-010 S | 0 | 0% | 0 | 0% | 0 | 0%
Labor - Soft Goods - Boxspring Cvr | 10-020 S | 0 | 0% | 0 | 0% | 0 | 0%
Labor - Soft Goods - Bedscarves | 10-030 S | 0 | 0% | 0 | 0% | 0 | 0%
Labor - Soft Goods - Pillows | 10-050 S | 0 | 0% | 0 | 0% | 0 | 0%
Labor - Soft Goods - Shower Curtains | 10-070 S | 0 | 0% | 0 | 0% | 0 | 0%
Labor - Soft Goods - Bed Bases *** | 10-080 L S | 0 | 0% | 0 | 0% | 0 | 0% | ***
Material - Soft Goods Fabric (CULP) | 10-040 M | 0 | 0% | 0 | 0% | 0 | 0%
Material - Soft Goods Fabric (BUY-IN) | 10-040 BI | 0 | 0% | 0 | 0% | 0 | 0%
Material - Soft Goods Lining (ALL) | 10-060 M | 0 | 0% | 0 | 0% | 0 | 0%
Material - Soft Goods Bed Bases | 10-080 M | 0 | 0% | 0 | 0% | 0 | 0%
|  | 89557.89 | 0% | 5101.63 | 4.243% | 94659.52 | 78.73%
SERVICES | ORIGINAL BUDGET |  |  | REVISIONS |  | CURRENT BUDGET |  |  | NOTES
Measure - Contract Services (Incl All Expenses Paid to Sub) | 09-010 S | 0 | 0% | 0 | 0% | 0 | 0%
Measure - RWP Labor Hours | 09-010 L | 0 | 0% | 0 | 0% | 0 | 0%
Measure - RWP Travel Expenses | 09-010 T | 0 |  | 0 |  | 0
Contract Labor - Installation (Incl All Expenses Paid to Sub) | 09-055 S | 0 | 0% | 0 | 0% | 0 | 0%
Installation - RWP Labor Hours | 09-055 L | 0 | 0% | 0 | 0% | 0 | 0%
Installation - RWP Travel | 09-055 T | 0 | 0% | 0 |  | 0
Installation - RWP Misc Supplies | 09-055 M | 0 | 0% | 0 |  | 0
Freight - Non-BiIIabIe (INCLD IN PRODUCT SALE) | 09-070 F | 0 | 0% | 0 | 0% | 0 | 0%
Freight - BiIIabIe | 09-080 F | 0 | 0% | 0 | 0% | 0 | 0%
Storage (INCL IN SALES EST) | 09-055 R | 0 | 0% | 0 | 0% | 0 | 0% |  | CommissionabIe SaIes | 120237.95
|  | 0 | 0% | 0 | 0% | 0 | 0% |  | SaIes Rep(s) | 0% | TotaI
[10 empty] | 0% | 0
| TOTAL COGS | 89557.89 | 0.74484 | 5101.63 | 4.243% | 94659.52 | 78.73% |  |  | 0% | 0
| NET PROFIT | 30680.06 | 0.25516 | 115136.32 | 95.76% | 25578.43 | 21.27% |  | Non-CuIp Buy-In Fabric Reduced From CommissionabIe SaIes
[9 empty] | Buy-In Fabric: | 0
[9 empty] | Lining Fabric: | 0