## Blocking Timeline
RENOVATION BLOCKING TIMELINE
| Association: |  | South Beach Resort Condominium Association, Inc.
| Resort: |  | South Beach Resort
| Project Name: |  | 2025 - SBR - Type ACD Renovation Bldgs E-H
| Renovation Start Date: |  | 2025-10-13
| Renovation Completion Date: |  | 2026-12-18
| Renovation Duration: |  | 431
| Renovation Type: |  | ACD
| Project Manager: |  | Christopher Chan
| Unit # | Unit Type | ADA | Building | Floor #
Building C | 124 | 2BD | No | Building C | 1
| 125 | 2BD | No | Building C | 1
| 126A | 2BD | No | Building C | 1
| 126B | 1BD | No | Building C | 1
| 221 | 2BD | No | Building C | 2
| 222 | 2BD | No | Building C | 2
| 223A | 2BD | No | Building C | 2
| 223B | 1BD | No | Building C | 2
| 224 | 2BD | No | Building C | 2
| 225 | 2BD | No | Building C | 2
| 226A | 2BD | No | Building C | 2
| 226B | 1BD | No | Building C | 2
| 321 | 2BD | No | Building C | 3
| 322 | 2BD | No | Building C | 3
| 323A | 2BD | No | Building C | 3
| 323B | 1BD | Yes | Building C | 3
| 324 | 2BD | No | Building C | 3
| 325 | 2BD | No | Building C | 3
| 326A | 2BD | No | Building C | 3
| 326B | 1BD | No | Building C | 3
| 421 | 2BD | No | Building C | 4
| 422 | 2BD | No | Building C | 4
| 423A | 2BD | Yes | Building C | 4
| 423B | 1BD | No | Building C | 4
| 424 | 2BD | No | Building C | 4
| 425 | 2BD | No | Building C | 4
| 426A | 2BD | No | Building C | 4
| 426B | 1BD | No | Building C | 4
Building D | 101 | 2BD | No | Building D | 1
| 102 | 2BD | No | Building D | 1
| 103A | 2BD | Yes | Building D | 1
| 103B | 1BD | No | Building D | 1
| 104 | 2BD | No | Building D | 1
| 105 | 2BD | No | Building D | 1
| 106A | 2BD | No | Building D | 1
| 106B | 1BD | No | Building D | 1
| 201 | 2BD | No | Building D | 2
| 202 | 2BD | No | Building D | 2
| 203A | 2BD | No | Building D | 2
| 203B | 1BD | No | Building D | 2
| 204 | 2BD | No | Building D | 2
| 205 | 2BD | No | Building D | 2
| 206A | 2BD | No | Building D | 2
| 206B | 1BD | Yes | Building D | 2
| 301 | 2BD | No | Building D | 3
| 302 | 2BD | No | Building D | 3
| 303A | 2BD | No | Building D | 3
| 303B | 1BD | No | Building D | 3
| 304 | 2BD | No | Building D | 3
| 305 | 2BD | No | Building D | 3
| 306A | 2BD | No | Building D | 3
| 306B | 1BD | No | Building D | 3
| 401 | 2BD | No | Building D | 4
| 402 | 2BD | No | Building D | 4
| 403A | 2BD | No | Building D | 4
| 403B | 1BD | No | Building D | 4
| 404 | 2BD | No | Building D | 4
| 405 | 2BD | No | Building D | 4
| 406A | 2BD | No | Building D | 4
| 406B | 1BD | No | Building D | 4
Building E | 111 | 2BD | Yes | Building E | 1
| 112 | 2BD | No | Building E | 1
| 113A | 2BD | No | Building E | 1
| 113B | 1BD | No | Building E | 1
| 114 | 2BD | No | Building E | 1
| 115 | 2BD | No | Building E | 1
| 116A | 2BD | No | Building E | 1
| 116B | 1BD | No | Building E | 1
| 211 | 2BD | No | Building E | 2
| 212 | 2BD | No | Building E | 2
| 213A | 2BD | No | Building E | 2
| 213B | 1BD | No | Building E | 2
| 214 | 2BD | No | Building E | 2
| 215 | 2BD | No | Building E | 2
| 216A | 2BD | No | Building E | 2
| 216B | 1BD | No | Building E | 2
| 311 | 2BD | No | Building E | 3
| 312 | 2BD | No | Building E | 3
| 313A | 2BD | No | Building E | 3
| 313B | 1BD | No | Building E | 3
| 314 | 2BD | No | Building E | 3
| 315 | 2BD | No | Building E | 3
| 316A | 2BD | No | Building E | 3
| 316B | 1BD | No | Building E | 3
| 411 | 2BD | No | Building E | 4
| 412 | 2BD | No | Building E | 4
| 413A | 2BD | No | Building E | 4
| 413B | 1BD | No | Building E | 4
| 414 | 2BD | No | Building E | 4
| 415 | 2BD | No | Building E | 4
| 416A | 2BD | No | Building E | 4
| 416B | 1BD | No | Building E | 4
Building F | 121 | 2BD | Yes | Building F | 1
| 122 | 2BD | No | Building F | 1
| 123A | 2BD | No | Building F | 1
| 123B | 1BD | No | Building F | 1
| 124 | 2BD | No | Building F | 1
| 125 | 2BD | No | Building F | 1
| 126A | 2BD | No | Building F | 1
| 126B | 1BD | No | Building F | 1
| 221 | 2BD | No | Building F | 2
| 222 | 2BD | No | Building F | 2
| 223A | 2BD | No | Building F | 2
| 223B | 1BD | No | Building F | 2
| 224 | 2BD | No | Building F | 2
| 225 | 2BD | No | Building F | 2
| 226A | 2BD | No | Building F | 2
| 226B | 1BD | No | Building F | 2
| 321 | 2BD | No | Building F | 3
| 322 | 2BD | No | Building F | 3
| 323A | 2BD | No | Building F | 3
| 323B | 1BD | No | Building F | 3
| 324 | 2BD | No | Building F | 3
| 325 | 2BD | No | Building F | 3
| 326A | 2BD | No | Building F | 3
| 326B | 1BD | No | Building F | 3
| 421 | 2BD | No | Building F | 4
| 422 | 2BD | No | Building F | 4
| 423A | 2BD | No | Building F | 4
| 423B | 1BD | No | Building F | 4
| 424 | 2BD | No | Building F | 4
| 425 | 2BD | No | Building F | 4
| 426A | 2BD | No | Building F | 4
| 426B | 1BD | No | Building F | 4
Building H | 211 | 2BD | No | Building H | 2
| 212 | 2BD | No | Building H | 2
| 213A | 2BD | No | Building H | 2
| 213B | 1BD | No | Building H | 2
| 214 | 2BD | No | Building H | 2
| 215 | 2BD | No | Building H | 2
| 216A | 2BD | No | Building H | 2
| 216B | 1BD | No | Building H | 2
| 311 | 2BD | No | Building H | 3
| 312 | 2BD | No | Building H | 3
| 313A | 2BD | No | Building H | 3
| 313B | 1BD | No | Building H | 3
| 314 | 2BD | No | Building H | 3
| 315 | 2BD | No | Building H | 3
| 316A | 2BD | No | Building H | 3
| 316B | 1BD | No | Building H | 3
| 411 | 2BD | No | Building H | 4
| 412 | 2BD | No | Building H | 4
| 413A | 2BD | No | Building H | 4
| 413B | 1BD | No | Building H | 4
| 414 | 2BD | No | Building H | 4
| 415 | 2BD | No | Building H | 4
| 416A | 2BD | No | Building H | 4
| 416B | 1BD | No | Building H | 4
Building G | 101 | 2BD | Yes | Building G | 1
| 102 | 2BD | No | Building G | 1
| 103A | 2BD | No | Building G | 1
| 103B | 1BD | No | Building G | 1
| 104 | 2BD | No | Building G | 1
| 105 | 2BD | No | Building G | 1
| 106A | 2BD | No | Building G | 1
| 106B | 1BD | No | Building G | 1
| 201 | 2BD | No | Building G | 2
| 202 | 2BD | No | Building G | 2
| 203A | 2BD | No | Building G | 2
| 203B | 1BD | No | Building G | 2
| 204 | 2BD | No | Building G | 2
| 205 | 2BD | No | Building G | 2
| 206A | 2BD | No | Building G | 2
| 206B | 1BD | No | Building G | 2
| 301 | 2BD | No | Building G | 3
| 302 | 2BD | No | Building G | 3
| 303A | 2BD | No | Building G | 3
| 303B | 1BD | No | Building G | 3
| 304 | 2BD | No | Building G | 3
| 305 | 2BD | No | Building G | 3
| 306A | 2BD | No | Building G | 3
| 306B | 1BD | No | Building G | 3
| 401 | 2BD | No | Building G | 4
| 402 | 2BD | No | Building G | 4
| 403A | 2BD | No | Building G | 4
| 403B | 1BD | No | Building G | 4
| 404 | 2BD | No | Building G | 4
| 405 | 2BD | No | Building G | 4
| 406A | 2BD | No | Building G | 4
| 406B | 1BD | No | Building G | 4
Phase 5 - (Units/Building)
Phase 6 - (Units/Building)
Phase 7 - (Units/Building)
Phase 8 - (Units/Building)
Phase 9 - (Units/Building)
Phase 10 - (Units/Building)
Note on D6: Chan, Christopher: Enter anticipated date for unit take down for project. This date should be inclusive of any days required for the resort to strip/defit the units.
Note on D7: Chan, Christopher: Enter anticipated date of completion. This date is inclusive of construction date, Housekeeping/AUM, and occupancy. This date should be the last phase occupancy date.