## Bid Form
Quotation |  |  | Quote #: | 25-106 REV4 price increase only
Attn: |  | Estimator | Date: | 2026-01-01
From: |  | Read Window Products, LLC | Project:
|  | 5900 Weisbrook Lane | #REF!
|  | Knoxville, TN 37909 | #REF!
Prepared by: |  | David Storm | Specification:
PH: 865-770-5812
FX: 865-675-5572
dstorm@readwindow.com
Estimate For: Motorized Shades on the 6th Floor
Description |  |  |  |  | Total w/Tax
16 |  | Draper Flexshade Motorized & Manual Shades with Recessed Headbox |  |  | 199690
Fabric: SW 4900 1% Color: TBD
Wirelss Wall Switch Included
Sales Tax, Freight and Installation included
Note: All Electrical or any LV wiring to be done by others
Estimate For: Manual Shades for 2nd, 3rd, 4th & 5th Floors (2nd Floor Quoted Recessed)
Description |  |  |  |  | Total w/Tax
193 |  | Draper Flexshade Manual Shades with Fascia |  |  | Included Above
Fabric: SW 4900 1% Color: TBD
Fascia Color: TBD
Standard Clutch Continuous Chain Loop Controls
Sales Tax, Freight and Installation included
Estimate For: Updated pricing with Cost increase for materials and labor for above base order
Description |  |  |  |  | Total Add w/Tax
209 |  | Updated pricing for Motorized and Manual shades for base bid |  |  | 7830
Total w/Tax
|  |  | New Total Contract Amount |  | 207520
Notes:
1. | Motorized roller shades will require 120v power via J-box or plug in outlet within 5' to 10' of each motor location. All electrical hardwiring, labor, materials & CONNECTIONS are to be provided by others. RWP to supply wall switches, but installation, wiring & connections of these components are to be provided by the Electrical Contractor as RWP is not licensed for this type of work. For Low Voltage Power will be needed for the Power panel and all LV wiring provided by others.
Terms & Conditions:
1. | Above prices are subject to increase unless confirmed by purchase order within
30 days of the above date.
2. | Delivery approximately 6 to 8 weeks from receipt of purchase order & all field measurements
3. | Payment Terms: 100% Prepayment for orders total less than $5K and 50% deposit for orders more than $5K. Balance due of Completed Production and/or Services Rendered.
4. | In the event of tax exempt status, a resale certificate must be included with the Purchase Order / Contract.
Sincerely,
David Storm
Read Window Products, LLC

## REV 4 Original Contract Amount
2026-01-01 |  |  |  | Quote # | 25-106 REV4 price increase only | [5 empty] | Cost: | 0
[11 empty] | Gross Margin: | 40% | 0
Read Window Products, LLC |  |  |  | Project: | 1620 Riverfront Parkway-CFC | [5 empty] | Tax: | 9.25% | 0
5900 Weisbrook Lane |  |  |  |  | Chattanooga TN | [7 empty] | 0
Knoxville, TN 37909 |  |  |  | Prepared by: | David Storm
865-770-5812
[5 empty] | dstorm@readwindow.com | [8 empty] | Total Revenue | 195574.61
Projections
[5 empty] | Style # | Price | Extended | Tax | Price |  | 43% |  |  |  |  | Total Cost Budget | Net Profit | Net Margin
Qty | Location | Width | Height | Product | Fabric/Color | Each | Total | 9.25% | Total | Cost | Margin |  |  | Ext Cost |  | 122178.19 | 73396.42 | 38%
2 | 6th Floor | 35 | 132 | Draper Motorized Shades | SW 4900 1% Color: TBD | 1015 | 2030 | 187.78 | 2217.78 | 578 | 1014.04 |  |  | 1156 |  | 64.17
1 | 6th Floor | 36 | 120 | Draper Motorized Shades | SW 4900 1% Color: TBD | 1001 | 1001 | 92.59 | 1093.59 | 570.03 | 1000.05 |  |  | 570.03 |  | 30
1 | 6th Floor | 39 | 132 | Draper Motorized Shades | SW 4900 1% Color: TBD | 1015 | 1015 | 93.89 | 1108.89 | 578 | 1014.04 |  |  | 578 |  | 35.75
2 | 6th Floor | 74 | 132 | Draper Motorized Shades | SW 4900 1% Color: TBD | 1358 | 2716 | 251.23 | 2967.23 | 774.03 | 1357.95 |  |  | 1548.06 |  | 135.67
5 | 6th Floor | 108 | 120 | Draper Motorized Shades | SW 4900 1% Color: TBD | 1660 | 8300 | 767.75 | 9067.75 | 945.72 | 1659.16 |  |  | 4728.6 |  | 450
2 | 6th Floor | 112 | 132 | Draper Motorized Shades | SW 4900 1% Color: TBD | 1744 | 3488 | 322.64 | 3810.64 | 993.64 | 1743.23 |  |  | 1987.28 |  | 205.33
1 | 6th Floor | 114 | 132 | Draper Motorized Shades | SW 4900 1% Color: TBD | 1744 | 1744 | 161.32 | 1905.32 | 993.64 | 1743.23 |  |  | 993.64 |  | 104.5
1 | 6th Floor | 160 (80+80) | 120 | Draper Motorized Shades | SW 4900 1% Color: TBD | 1822 | 1822 | 168.54 | 1990.54 | 1038.46 | 1821.86 |  |  | 1038.46 |  | #VALUE!
1 | 6th Floor | 204 (81.5+41+81.5) | 132 | Draper Motorized Shades | SW 4900 1% Color: TBD | 2215 | 2215 | 204.89 | 2419.89 | 1262.12 | 2214.25 |  |  | 1262.12 |  | #VALUE!
1 |  |  |  | Motor Controls & Switches |  | 7674 | 7674 | 709.85 | 8383.85 | 4374 | 7673.68 |  |  | 4374 |  | 0
1 |  |  |  | Recessed Headbox |  | 19151 | 19151 | 1771.47 | 20922.47 | 10915.56 | 19150.11 |  |  | 10915.56 |  | 0
5 | 2nd Floor | 28 | 132 | Draper Manual Shades | SW 4900 1% Color: TBD | 239 | 1195 | 110.54 | 1305.54 | 135.96 | 238.53 |  |  | 679.8 |  | 128.33
10 | 2nd Floor | 60 | 132 | Draper Manual Shades | SW 4900 1% Color: TBD | 424 | 4240 | 392.2 | 4632.2 | 241.17 | 423.11 |  |  | 2411.7 |  | 550
5 | 2nd Floor | 86 | 132 | Draper Manual Shades | SW 4900 1% Color: TBD | 654 | 3270 | 302.48 | 3572.48 | 372.66 | 653.79 |  |  | 1863.3 |  | 394.17
38 | 2nd Floor | 60 | 132 | Draper Manual Shades | SW 4900 1% Color: TBD | 424 | 16112 | 1490.36 | 17602.36 | 241.17 | 423.11 |  |  | 9164.46 |  | 2090
3 | 3rd, 4th & 5th Floors | 24 | 96 | Draper Manual Shades | SW 4900 1% Color: TBD | 200 | 600 | 55.5 | 655.5 | 113.45 | 199.04 |  |  | 340.35 |  | 48
36 | 3rd, 4th & 5th Floors | 36 | 96 | Draper Manual Shades | SW 4900 1% Color: TBD | 235 | 8460 | 782.55 | 9242.55 | 133.4 | 234.04 |  |  | 4802.4 |  | 864
39 | 3rd, 4th & 5th Floors | 54 | 90 | Draper Manual Shades | SW 4900 1% Color: TBD | 291 | 11349 | 1049.78 | 12398.78 | 165.33 | 290.05 |  |  | 6447.87 |  | 1316.25
6 | 3rd, 4th & 5th Floors | 60 | 96 | Draper Manual Shades | SW 4900 1% Color: TBD | 309 | 1854 | 171.5 | 2025.5 | 176.09 | 308.93 |  |  | 1056.54 |  | 240
9 | 3rd, 4th & 5th Floors | 96 | 90 | Draper Manual Shades | SW 4900 1% Color: TBD | 489 | 4401 | 407.09 | 4808.09 | 278.66 | 488.88 |  |  | 2507.94 |  | 540
42 | 3rd, 4th & 5th Floors | 108 | 90 | Draper Manual Shades | SW 4900 1% Color: TBD | 631 | 26502 | 2451.44 | 28953.44 | 359.54 | 630.77 |  |  | 15100.68 |  | 2835
[14 empty] | 0 |  | 0
16 |  |  |  | Install Motorized Shade |  | 75 | 1200 |  | 1200 | 50 | 66.67 | 25% |  | 800 |  | Minimum cost $12.50 ea for in house install, $25 each for subcontractor installed
193 |  |  |  | Install Manual Shade |  | 50 | 9650 |  | 9650 | 35 | 46.67 | 25% |  | 6755 |  | Minimum cost $12.50 ea for in house install, $25 each for subcontractor installed
55 |  |  |  | Install Recessed Headbox |  | 100 | 5500 |  | 5500 | 75 | 100 | 25% |  | 4125 |  | Minimum cost $12.50 ea for in house install, $25 each for subcontractor installed
1 |  |  |  | Programing Fee |  | 1500 | 1500 |  | 1500 | 1000 | 1333.33 |  |  | 1000 |  | In house: # of hours X's $25/hr. Minimum $350 per day subcontractor measure
1 |  |  |  | Measure |  | 650 | 650 |  | 650 | 500 | 500 |  |  | 500 |  | -
1 |  |  |  | Measure Trip Charge Budget (Mileage, Time) |  | 750 | 750 |  | 750 | 347.4 | 463.2 |  |  | 347.4 |  | -
1 |  |  |  | Install Trip Charge Budget (Mileage, Time) |  | 33850 | 33850 |  | 33850 | 25374 | 33832 |  |  | 25374 |  | -
1 |  |  |  | Freight Budget |  | 13335.61 | 13335.61 |  | 13335.61 | 9750 | 13000 |  |  | 9750 |  | -
[7 empty] | 195574.61 | 11945.39 | 207520
*** Remember to include lodging in trip estimates, if required
*** Edit product / service descriptions as needed. Pricing will self populate once you enter Cost in Column L
*** Please update Sales Tax Rate to the specific State & County for which the project is located

## REV 4 & CO1 Detailed match BMX
2026-01-01 |  |  |  | Quote # | 25-106 REV4 & CO1 | [5 empty] | Cost: | 0
[11 empty] | Gross Margin: | 40% | 0
Read Window Products, LLC |  |  |  | Project: | 1620 Riverfront Parkway-CFC | [5 empty] | Tax: | 9.25% | 0
5900 Weisbrook Lane |  |  |  |  | Chattanooga TN | [7 empty] | 0
Knoxville, TN 37909 |  |  |  | Prepared by: | David Storm
865-770-5812
[5 empty] | dstorm@readwindow.com | [8 empty] | Total Revenue | 216194.37
Projections
[5 empty] | Style # | Price | Extended | Tax | Price |  | 45% | 53% |  |  |  | Total Cost Budget | Net Profit | Net Margin
Qty | Location | Width | Height | Product | Fabric/Color | Each | Total | 9.25% | Total | Cost | Margin |  |  | Ext Cost |  | 128405.4 | 87788.97 | 41%
2 | 6th Floor | 35 | 132 | Draper Motorized Shades | SW 2500 1% Color: Oyster/Pearl Grey | 1229.79 | 2459.58 | 227.51 | 2687.09 | 578 | 1229.79 |  |  | 1156 |  | 64.17
1 | 6th Floor | 36 | 120 | Draper Motorized Shades | SW 2500 1% Color: Oyster/Pearl Grey | 1212.83 | 1212.83 | 112.19 | 1325.02 | 570.03 | 1212.83 |  |  | 570.03 |  | 30
1 | 6th Floor | 39 | 132 | Draper Motorized Shades | SW 2500 1% Color: Oyster/Pearl Grey | 1229.79 | 1229.79 | 113.76 | 1343.55 | 578 | 1229.79 |  |  | 578 |  | 35.75
2 | 6th Floor | 74 | 132 | Draper Motorized Shades | SW 2500 1% Color: Oyster/Pearl Grey | 1646.87 | 3293.74 | 304.67 | 3598.41 | 774.03 | 1646.87 |  |  | 1548.06 |  | 135.67
5 | 6th Floor | 108 | 120 | Draper Motorized Shades | SW 2500 1% Color: Oyster/Pearl Grey | 2012.17 | 10060.85 | 930.63 | 10991.48 | 945.72 | 2012.17 |  |  | 4728.6 |  | 450
2 | 6th Floor | 112 | 132 | Draper Motorized Shades | SW 2500 1% Color: Oyster/Pearl Grey | 2114.13 | 4228.26 | 391.11 | 4619.37 | 993.64 | 2114.13 |  |  | 1987.28 |  | 205.33
1 | 6th Floor | 114 | 132 | Draper Motorized Shades | SW 2500 1% Color: Oyster/Pearl Grey | 2114.13 | 2114.13 | 195.56 | 2309.69 | 993.64 | 2114.13 |  |  | 993.64 |  | 104.5
1 | 6th Floor | 160 (80+80) | 120 | Draper Motorized Shades | SW 2500 1% Color: Oyster/Pearl Grey | 2209.49 | 2209.49 | 204.38 | 2413.87 | 1038.46 | 2209.49 |  |  | 1038.46 |  | #VALUE!
1 | 6th Floor | 204 (81.5+41+81.5) | 132 | Draper Motorized Shades | SW 2500 1% Color: Oyster/Pearl Grey | 2685.36 | 2685.36 | 248.4 | 2933.76 | 1262.12 | 2685.36 |  |  | 1262.12 |  | #VALUE!
6 | 6th Floor | 54 | 120 | Draper Manual Shades | SW 2500 1% Color: Oyster/Pearl Grey | 408.4 | 2450.4 | 226.66 | 2677.06 | 224.62 | 408.4 |  |  | 1347.72 |  | 270
6 | 6th Floor | 74 | 132 | Draper Manual Shades | SW 2500 1% Color: Oyster/Pearl Grey | 537.07 | 3222.42 | 298.07 | 3520.49 | 295.39 | 537.07 |  |  | 1772.34 |  | 407
6 | 6th Floor | 80 | 132 | Draper Manual Shades | SW 2500 1% Color: Oyster/Pearl Grey | 537.07 | 3222.42 | 298.07 | 3520.49 | 295.39 | 537.07 |  |  | 1772.34 |  | 440
1 | 6th Floor | 96 | 132 | Draper Manual Shades | SW 2500 1% Color: Oyster/Pearl Grey | 677.56 | 677.56 | 62.67 | 740.23 | 372.66 | 677.56 |  |  | 372.66 |  | 88
1 | 6th Floor | 40 | 132 | Draper Manual Shades | SW 2500 1% Color: Oyster/Pearl Grey | 294.33 | 294.33 | 27.23 | 321.56 | 161.88 | 294.33 |  |  | 161.88 |  | 36.67
1 |  |  |  | Recessed Headbox for 6th Floor Manual (8) |  | 3934.33 | 3934.33 | 363.93 | 4298.26 | 2163.88 | 3934.33 |  |  | 2163.88 |  | 0
1 |  |  |  | Recessed Headbox for 6th Floor Manual Credit (QTY 4) (6-28 Corridor B) (Includes add of surface headbox) |  | 1606.04 | 1606.04 | 148.56 | 1754.6 | 883.32 | 1606.04 |  |  | 883.32 |  | 0
8 |  |  |  | Wireless Wall Switches |  | 308.51 | 2468.08 | 228.3 | 2696.38 | 145 | 308.51 |  |  | 1160 |  | 0
1 |  |  |  | Recessed Headbox Motorized 6th FL and Manual 2nd FL (36) |  | 17727.05 | 17727.05 | 1639.75 | 19366.8 | 9749.88 | 17727.05 |  |  | 9749.88 |  | 0
1 |  |  |  | Recessed Headbox Motorized 6th FL Credit (QTY 6) (Rooms 6-22 & 6-10) (Includes add of surface headbox) |  | 2409.05 | 2409.05 | 222.84 | 2631.89 | 1324.98 | 2409.05 |  |  | 1324.98 |  | 0
5 | 2nd Floor | 28 | 132 | Draper Manual Shades | SW 2500 1% Color: Oyster/Pearl Grey | 247.2 | 1236 | 114.33 | 1350.33 | 135.96 | 247.2 |  |  | 679.8 |  | 128.33
9 | 2nd Floor | 60 | 132 | Draper Manual Shades | SW 2500 1% Color: Oyster/Pearl Grey | 438.49 | 3946.41 | 365.04 | 4311.45 | 241.17 | 438.49 |  |  | 2170.53 |  | 495
5 | 2nd Floor | 86 | 132 | Draper Manual Shades | SW 2500 1% Color: Oyster/Pearl Grey | 677.56 | 3387.8 | 313.37 | 3701.17 | 372.66 | 677.56 |  |  | 1863.3 |  | 394.17
36 | 2nd Floor | 60 | 132 | Draper Manual Shades | SW 2500 1% Color: Oyster/Pearl Grey | 438.49 | 15785.64 | 1460.17 | 17245.81 | 241.17 | 438.49 |  |  | 8682.12 |  | 1980
3 | 2nd Floor | 108 | 120 | Draper Manual Shades with Fascia | SW 2500 1% Color: Oyster/Pearl Grey | 859.2 | 2577.6 | 238.43 | 2816.03 | 472.56 | 859.2 |  |  | 1417.68 |  | 270
2 | 2nd Floor | 60 | 120 | Draper Manual Shades with Fascia | SW 2500 1% Color: Oyster/Pearl Grey | 429.78 | 859.56 | 79.51 | 939.07 | 236.38 | 429.78 |  |  | 472.76 |  | 100
1 | 3rd Floor Shades (34 Shades) |  |  | Draper Manual Shades | Bedrooms - SW 7500 0% Color: Mist Living RM's SW 2500 1% Color: Oyster/Pearl Grey | 12195.18 | 12195.18 | 1128.05 | 13323.23 | 6707.35 | 12195.18 |  |  | 6707.35 |  | 0
1 | 4th Floor Shades (34 Shades) |  |  | Draper Manual Shades | Bedrooms - SW 7500 0% Color: Mist Living RM's SW 2500 1% Color: Oyster/Pearl Grey | 12432 | 12432 | 1149.96 | 13581.96 | 6837.6 | 12432 |  |  | 6837.6 |  | 0
1 | 5th Floor Shades(34 Shades) |  |  | Draper Manual Shades | Bedrooms - SW 7500 0% Color: Mist Living RM's SW 2500 1% Color: Oyster/Pearl Grey | 12432 | 12432 | 1149.96 | 13581.96 | 6837.6 | 12432 |  |  | 6837.6 |  | 0
11 | 3rd Floor Credit for 11 Shades | 35 | 93 | Draper Manual Shades Credit | SW 2500 1% Color: Oyster/Pearl Grey | 246.53 | 2711.83 | 250.84 | 2962.67 | 135.59 | 246.53 |  |  | 1491.49 |  | 248.65
11 | 4th Floor Credit for 11 Shades | 35 | 93 | Draper Manual Shades Credit | SW 2500 1% Color: Oyster/Pearl Grey | 246.53 | 2711.83 | 250.84 | 2962.67 | 135.59 | 246.53 |  |  | 1491.49 |  | 248.65
11 | 5th Floor Credit for 11 Shades | 35 | 93 | Draper Manual Shades Credit | SW 2500 1% Color: Oyster/Pearl Grey | 246.53 | 2711.83 | 250.84 | 2962.67 | 135.59 | 246.53 |  |  | 1491.49 |  | 248.65
[14 empty] | 0 |  | 0
16 |  |  |  | Install Motorized Shades 6th Floor |  | 75 | 1200 |  | 1200 | 50 | 66.67 | 25% |  | 800 |  | Minimum cost $12.50 ea for in house install, $25 each for subcontractor installed
34 |  |  |  | Install Manual Shade 3rd Floor |  | 50 | 1700 |  | 1700 | 35 | 46.67 | 25% |  | 1190 |  | Minimum cost $12.50 ea for in house install, $25 each for subcontractor installed
34 |  |  |  | Install Manual Shade 4th Floor |  | 50 | 1700 |  | 1700 | 35 | 46.67 | 25% |  | 1190 |  | Minimum cost $12.50 ea for in house install, $25 each for subcontractor installed
34 |  |  |  | Install Manual Shade 5th Floor |  | 50 | 1700 |  | 1700 | 35 | 46.67 | 25% |  | 1190 |  | Minimum cost $12.50 ea for in house install, $25 each for subcontractor installed
33 |  |  |  | Credit for Install Labor 3rd,4th, &5th Floors |  | 50 | 1650 |  | 1650 | 35 | 46.67 | 25% |  | 1155 |  | Minimum cost $12.50 ea for in house install, $25 each for subcontractor installed
80 |  |  |  | Install Manual Shades 6th FL & 2nd FL (This included Credits and Adds from Change Order 1) |  | 50 | 4000 |  | 4000 | 35 | 46.67 | 25% |  | 2800 |  | Minimum cost $12.50 ea for in house install, $25 each for subcontractor installed
27 |  |  |  | Install Recessed Headbox 2nd Floor |  | 100 | 2700 |  | 2700 | 75 | 100 | 25% |  | 2025 |  | Minimum cost $12.50 ea for in house install, $25 each for subcontractor installed
9 |  |  |  | Install Recessed Headbox 6th Fl Motorized (QTY 9) |  | 100 | 900 |  | 900 | 75 | 100 | 25% |  | 675 |  | Minimum cost $12.50 ea for in house install, $25 each for subcontractor installed
6 |  |  |  | Install Recessed Headbox 6th Fl Motorized Credit (QTY 6) (Rooms 6-22 & 6-10) |  | 100 | 600 |  | 600 | 75 | 100 | 25% |  | 450 |  | Minimum cost $12.50 ea for in house install, $25 each for subcontractor installed
8 |  |  |  | Install Recessed Headbox 6th FL Manual (QTY 8) |  | 100 | 800 |  | 800 | 75 | 100 | 25% |  | 600 |  | Minimum cost $12.50 ea for in house install, $25 each for subcontractor installed
4 |  |  |  | Install Recessed Headbox 6th FL Manual Credit (QTY 4) (6-28 Corridor B) |  | 100 | 400 |  | 400 | 75 | 100 | 25% |  | 300 |  | Minimum cost $12.50 ea for in house install, $25 each for subcontractor installed
1 |  |  |  | Motorized Programing Fee |  | 2500 | 2500 |  | 2500 | 1000 | 1333.33 |  |  | 1000 |  | In house: # of hours X's $25/hr. Minimum $350 per day subcontractor measure
1 |  |  |  | Measure Fee |  | 750 | 750 |  | 750 | 550 | 733.33 |  |  | 550 |  | -
1 |  |  |  | Measure Trip Charge Budget (Mileage, Time) |  | 2200 | 2200 |  | 2200 | 1616 | 2154.67 |  |  | 1616 |  | -
1 |  |  |  | 2nd FL Install Trip Charge Budget |  | 10675 | 10675 |  | 10675 | 7500 | 10000 |  |  | 7500 |  | -
1 |  |  |  | 3rd FL Install Trip Charge Budget |  | 4500 | 4500 |  | 4500 | 3350 | 4466.67 |  |  | 3350 |  | -
1 |  |  |  | 4th FL Install Trip Charge Budget |  | 4500 | 4500 |  | 4500 | 3350 | 4466.67 |  |  | 3350 |  | -
1 |  |  |  | 5th FL Install Trip Charge Budget |  | 4500 | 4500 |  | 4500 | 3350 | 4466.67 |  |  | 3350 |  | -
1 |  |  |  | 6th FL Install Trip Charge Budget |  | 10675 | 10675 |  | 10675 | 7500 | 10000 |  |  | 7500 |  | -
1 |  |  |  | 2nd FL Freight |  | 5500.76 | 5500.76 |  | 5500.76 | 4000 | 5333.33 |  |  | 4000 |  | -
1 |  |  |  | 3rd FL Freight |  | 2349.82 | 2349.82 |  | 2349.82 | 1700 | 2266.67 |  |  | 1700 |  | -
1 |  |  |  | 4th FL Freight |  | 2349.82 | 2349.82 |  | 2349.82 | 1700 | 2266.67 |  |  | 1700 |  | -
1 |  |  |  | 5th FL Freight |  | 2349.82 | 2349.82 |  | 2349.82 | 1700 | 2266.67 |  |  | 1700 |  | -
1 |  |  |  | 6th FL Freight |  | 5500.76 | 5500.76 |  | 5500.76 | 4000 | 5333.33 |  |  | 4000 |  | -
[7 empty] | 216194.37 | 12995.63 | 229190
*** Remember to include lodging in trip estimates, if required
*** Edit product / service descriptions as needed. Pricing will self populate once you enter Cost in Column L
*** Please update Sales Tax Rate to the specific State & County for which the project is located

## CO2 updated SOV for BMX
2026-01-01 |  |  |  | Quote # | 25-106 CO2 Updated SOV | [5 empty] | Cost: | 0
[11 empty] | Gross Margin: | 40% | 0
Read Window Products, LLC |  |  |  | Project: | 1620 Riverfront Parkway-CFC | [5 empty] | Tax: | 9.25% | 0
5900 Weisbrook Lane |  |  |  |  | Chattanooga TN | [7 empty] | 0
Knoxville, TN 37909 |  |  |  | Prepared by: | David Storm
865-770-5812
[5 empty] | dstorm@readwindow.com | [8 empty] | Total Revenue | 205152.93
Projections
[5 empty] | Style # | Price | Extended | Tax | Price |  | 45% | 53% | 60% |  |  | Total Cost Budget | Net Profit | Net Margin
Qty | Location | Width | Height | Product | Fabric/Color | Each | Total | 9.25% | Total | Cost | Margin |  |  | Ext Cost |  | 121878.63 | 83274.3 | 41%
2 | 6th Floor | 35 | 132 | Draper Motorized Shades | SW 2500 1% Color: Oyster/Pearl Grey | 1229.79 | 2459.58 | 227.51 | 2687.09 | 578 | 1229.79 |  |  | 1156 |  | 64.17
1 | 6th Floor | 36 | 120 | Draper Motorized Shades | SW 2500 1% Color: Oyster/Pearl Grey | 1212.83 | 1212.83 | 112.19 | 1325.02 | 570.03 | 1212.83 |  |  | 570.03 |  | 30
1 | 6th Floor | 39 | 132 | Draper Motorized Shades | SW 2500 1% Color: Oyster/Pearl Grey | 1229.79 | 1229.79 | 113.76 | 1343.55 | 578 | 1229.79 |  |  | 578 |  | 35.75
2 | 6th Floor | 74 | 132 | Draper Motorized Shades | SW 2500 1% Color: Oyster/Pearl Grey | 1646.87 | 3293.74 | 304.67 | 3598.41 | 774.03 | 1646.87 |  |  | 1548.06 |  | 135.67
5 | 6th Floor | 108 | 120 | Draper Motorized Shades | SW 2500 1% Color: Oyster/Pearl Grey | 2012.17 | 10060.85 | 930.63 | 10991.48 | 945.72 | 2012.17 |  |  | 4728.6 |  | 450
2 | 6th Floor | 112 | 132 | Draper Motorized Shades | SW 2500 1% Color: Oyster/Pearl Grey | 2114.13 | 4228.26 | 391.11 | 4619.37 | 993.64 | 2114.13 |  |  | 1987.28 |  | 205.33
1 | 6th Floor | 114 | 132 | Draper Motorized Shades | SW 2500 1% Color: Oyster/Pearl Grey | 2114.13 | 2114.13 | 195.56 | 2309.69 | 993.64 | 2114.13 |  |  | 993.64 |  | 104.5
1 | 6th Floor | 160 (80+80) | 120 | Draper Motorized Shades | SW 2500 1% Color: Oyster/Pearl Grey | 2209.49 | 2209.49 | 204.38 | 2413.87 | 1038.46 | 2209.49 |  |  | 1038.46 |  | #VALUE!
1 | 6th Floor | 204 (81.5+41+81.5) | 132 | Draper Motorized Shades | SW 2500 1% Color: Oyster/Pearl Grey | 2685.36 | 2685.36 | 248.4 | 2933.76 | 1262.12 | 2685.36 |  |  | 1262.12 |  | #VALUE!
1 | 6-24 | 114 | 120 | Draper Motorized Shades | SW 2500 1% Color: Oyster/Pearl Grey | 1987.27 | 1987.27 | 183.82 | 2171.09 | 1093 | 1987.27 |  |  | 1093 |  | 95
6 | 6th Floor | 54 | 120 | Draper Manual Shades | SW 2500 1% Color: Oyster/Pearl Grey | 408.4 | 2450.4 | 226.66 | 2677.06 | 224.62 | 408.4 |  |  | 1347.72 |  | 270
6 | 6th Floor | 74 | 132 | Draper Manual Shades | SW 2500 1% Color: Oyster/Pearl Grey | 537.07 | 3222.42 | 298.07 | 3520.49 | 295.39 | 537.07 |  |  | 1772.34 |  | 407
6 | 6th Floor | 80 | 132 | Draper Manual Shades | SW 2500 1% Color: Oyster/Pearl Grey | 537.07 | 3222.42 | 298.07 | 3520.49 | 295.39 | 537.07 |  |  | 1772.34 |  | 440
1 | 6th Floor | 96 | 132 | Draper Manual Shades | SW 2500 1% Color: Oyster/Pearl Grey | 677.56 | 677.56 | 62.67 | 740.23 | 372.66 | 677.56 |  |  | 372.66 |  | 88
1 | 6th Floor | 40 | 132 | Draper Manual Shades | SW 2500 1% Color: Oyster/Pearl Grey | 294.33 | 294.33 | 27.23 | 321.56 | 161.88 | 294.33 |  |  | 161.88 |  | 36.67
1 |  |  |  | Recessed Headbox for 6th Floor Manual (8) |  | 3934.33 | 3934.33 | 363.93 | 4298.26 | 2163.88 | 3934.33 |  |  | 2163.88 |  | 0
8 |  |  |  | Wireless Wall Switches |  | 308.51 | 2468.08 | 228.3 | 2696.38 | 145 | 308.51 |  |  | 1160 |  | 0
1 |  |  |  | Recessed Headbox Motorized 6th FL (9) |  | 4431.76 | 4431.76 | 409.94 | 4841.7 | 2437.47 | 4431.76 |  |  | 2437.47 |  | 0
1 |  |  |  | Recessed Headbox Manual 2nd FL (27) |  | 13295.29 | 13295.29 | 1229.81 | 14525.1 | 7312.41 | 13295.29 |  |  | 7312.41 |  | 0
6 |  |  |  | 5" Closure (147" Stock Lengths) |  | 132.5 | 795 | 73.54 | 868.54 | 53 | 132.5 |  |  | 318 |  | 0
5 | 2nd Floor | 28 | 132 | Draper Manual Shades | SW 2500 1% Color: Oyster/Pearl Grey | 247.2 | 1236 | 114.33 | 1350.33 | 135.96 | 247.2 |  |  | 679.8 |  | 128.33
9 | 2nd Floor | 60 | 132 | Draper Manual Shades | SW 2500 1% Color: Oyster/Pearl Grey | 438.49 | 3946.41 | 365.04 | 4311.45 | 241.17 | 438.49 |  |  | 2170.53 |  | 495
5 | 2nd Floor | 86 | 132 | Draper Manual Shades | SW 2500 1% Color: Oyster/Pearl Grey | 677.56 | 3387.8 | 313.37 | 3701.17 | 372.66 | 677.56 |  |  | 1863.3 |  | 394.17
36 | 2nd Floor | 60 | 132 | Draper Manual Shades | SW 2500 1% Color: Oyster/Pearl Grey | 438.49 | 15785.64 | 1460.17 | 17245.81 | 241.17 | 438.49 |  |  | 8682.12 |  | 1980
3 | 2nd Floor | 108 | 120 | Draper Manual Shades with Fascia | SW 2500 1% Color: Oyster/Pearl Grey | 859.2 | 2577.6 | 238.43 | 2816.03 | 472.56 | 859.2 |  |  | 1417.68 |  | 270
2 | 2nd Floor | 60 | 120 | Draper Manual Shades with Fascia | SW 2500 1% Color: Oyster/Pearl Grey | 429.78 | 859.56 | 79.51 | 939.07 | 236.38 | 429.78 |  |  | 472.76 |  | 100
1 | 3rd Floor Shades (34 Shades) |  |  | Draper Manual Shades | Bedrooms - SW 7500 0% Color: Mist Living RM's SW 2500 1% Color: Oyster/Pearl Grey | 12195.18 | 12195.18 | 1128.05 | 13323.23 | 6707.35 | 12195.18 |  |  | 6707.35 |  | 0
1 | 4th Floor Shades (34 Shades) |  |  | Draper Manual Shades | Bedrooms - SW 7500 0% Color: Mist Living RM's SW 2500 1% Color: Oyster/Pearl Grey | 12432 | 12432 | 1149.96 | 13581.96 | 6837.6 | 12432 |  |  | 6837.6 |  | 0
1 | 5th Floor Shades(34 Shades) |  |  | Draper Manual Shades | Bedrooms - SW 7500 0% Color: Mist Living RM's SW 2500 1% Color: Oyster/Pearl Grey | 12432 | 12432 | 1149.96 | 13581.96 | 6837.6 | 12432 |  |  | 6837.6 |  | 0
[14 empty] | 0 |  | 0
17 |  |  |  | Install Motorized Shades 6th Floor & RM 6-24 |  | 75 | 1275 |  | 1275 | 50 | 66.67 | 25% |  | 850 |  | Minimum cost $12.50 ea for in house install, $25 each for subcontractor installed
34 |  |  |  | Install Manual Shade 3rd Floor |  | 50 | 1700 |  | 1700 | 35 | 46.67 | 25% |  | 1190 |  | Minimum cost $12.50 ea for in house install, $25 each for subcontractor installed
34 |  |  |  | Install Manual Shade 4th Floor |  | 50 | 1700 |  | 1700 | 35 | 46.67 | 25% |  | 1190 |  | Minimum cost $12.50 ea for in house install, $25 each for subcontractor installed
34 |  |  |  | Install Manual Shade 5th Floor |  | 50 | 1700 |  | 1700 | 35 | 46.67 | 25% |  | 1190 |  | Minimum cost $12.50 ea for in house install, $25 each for subcontractor installed
80 |  |  |  | Install Manual Shades 6th FL & 2nd FL (This included Credits and Adds from Change Order 1) |  | 50 | 4000 |  | 4000 | 35 | 46.67 | 25% |  | 2800 |  | Minimum cost $12.50 ea for in house install, $25 each for subcontractor installed
27 |  |  |  | Install Recessed Headbox 2nd Floor |  | 100 | 2700 |  | 2700 | 75 | 100 | 25% |  | 2025 |  | Minimum cost $12.50 ea for in house install, $25 each for subcontractor installed
9 |  |  |  | Install Recessed Headbox 6th Fl Motorized (QTY 9) |  | 100 | 900 |  | 900 | 75 | 100 | 25% |  | 675 |  | Minimum cost $12.50 ea for in house install, $25 each for subcontractor installed
8 |  |  |  | Install Recessed Headbox 6th FL Manual (QTY 8) |  | 100 | 800 |  | 800 | 75 | 100 | 25% |  | 600 |  | Minimum cost $12.50 ea for in house install, $25 each for subcontractor installed
40 |  |  |  | Install 5" Closure in open areas with no shades |  | 20 | 800 |  | 800 | 15 | 20 | 25% |  | 600 |  | Minimum cost $12.50 ea for in house install, $25 each for subcontractor installed
1 |  |  |  | Motorized Programing Fee |  | 2500 | 2500 |  | 2500 | 1000 | 1333.33 |  |  | 1000 |  | In house: # of hours X's $25/hr. Minimum $350 per day subcontractor measure
1 |  |  |  | Measure Fee |  | 750 | 750 |  | 750 | 550 | 733.33 |  |  | 550 |  | -
1 |  |  |  | Measure Trip Charge Budget (Mileage, Time) |  | 2200 | 2200 |  | 2200 | 1616 | 2154.67 |  |  | 1616 |  | -
1 |  |  |  | 2nd FL Install Trip Charge Budget Shades |  | 5337.5 | 5337.5 |  | 5337.5 | 3750 | 5000 |  |  | 3750 |  | -
1 |  |  |  | 2nd FL Install Trip Charge Budget Headboxes |  | 5337.5 | 5337.5 |  | 5337.5 | 3750 | 5000 |  |  | 3750 |  | -
1 |  |  |  | 3rd FL Install Trip Charge Budget |  | 4500 | 4500 |  | 4500 | 3350 | 4466.67 |  |  | 3350 |  | -
1 |  |  |  | 4th FL Install Trip Charge Budget |  | 4500 | 4500 |  | 4500 | 3350 | 4466.67 |  |  | 3350 |  | -
1 |  |  |  | 5th FL Install Trip Charge Budget |  | 4500 | 4500 |  | 4500 | 3350 | 4466.67 |  |  | 3350 |  | -
1 |  |  |  | 6th FL Install Trip Charge Budget Shades |  | 5337.5 | 5337.5 |  | 5337.5 | 3750 | 5000 |  |  | 3750 |  | -
1 |  |  |  | 6th FL Install Trip Charge Budget Headboxes |  | 5337.5 | 5337.5 |  | 5337.5 | 3750 | 5000 |  |  | 3750 |  | -
1 |  |  |  | 2nd FL Freight Shades |  | 2750.38 | 2750.38 |  | 2750.38 | 2000 | 2666.67 |  |  | 2000 |  | -
1 |  |  |  | 2nd FL Freight Headboxes & 5" Closure |  | 2852.25 | 2852.25 |  | 2852.25 | 2000 | 2666.67 |  |  | 2000 |  | -
1 |  |  |  | 3rd FL Freight |  | 2349.82 | 2349.82 |  | 2349.82 | 1700 | 2266.67 |  |  | 1700 |  | -
1 |  |  |  | 4th FL Freight |  | 2349.82 | 2349.82 |  | 2349.82 | 1700 | 2266.67 |  |  | 1700 |  | -
1 |  |  |  | 5th FL Freight |  | 2349.82 | 2349.82 |  | 2349.82 | 1700 | 2266.67 |  |  | 1700 |  | -
1 |  |  |  | 6th FL Freight Shades |  | 2750.38 | 2750.38 |  | 2750.38 | 2000 | 2666.67 |  |  | 2000 |  | -
1 |  |  |  | 6th FL Freight Headboxes |  | 2750.38 | 2750.38 |  | 2750.38 | 2000 | 2666.67 |  |  | 2000 |  | -
[7 empty] | 205152.93 | 12129.07 | 217282
*** Remember to include lodging in trip estimates, if required
*** Edit product / service descriptions as needed. Pricing will self populate once you enter Cost in Column L
*** Please update Sales Tax Rate to the specific State & County for which the project is located

## Glossary
Installation Time (based on 2 man crew) | # per Day | Budget Install Labor Rates (cost) | Gross Product & Install Margin Structure
Horizontal Louver Blinds | 50 | 20
Single Manual Roller Shades w/Fascia | 40 | 25 |  | Product & Install Value | Margin
Dual Manual Roller Shades 2/Fascia | 25 | 40 |  | < $5,000 | No Bid
Recessed Pocket | 20 | $3/ft |  | $5,000 - $10,000 | 40%
Single Motorized Shade Band w/Fascia | 10 | 50 |  | $10,000 - $15,000 | 30%
Dual Motorized Shade w/Fascia | ask David | 80 |  | $15,000 - $25,000 | 25%
Cubicle Curtains w/ Tracks | 20 | $3/ft |  | >$25,000 | ask David or Wes
Shutters |  | 75
*** Above to be used as guide on product & required install for all manually operated product (NOT MOTORIZED)
Product Descriptions:
Single Manual Clutch Rolle Shade w/ Fascia
Dual Manual Clutch Roller Shade w/ Fascia
Single Motorized Roller Shade w/ Fascia
Dual Motorized Roller Shade w/ Fascia
120v Motorized Operation
Battery Powered Operation
120v Wall Switch Control
Low Voltage Wall Switch Control
Horizontal Louver Blinds
2" Faux Wood Horizontal Louver Blinds
Miscellaneous Notes to be included on Bids:
*** Recessed mount roller shades will required continuous & level wood blocking. Blocking to be provided by OTHERS.
*** Motorized roller shades will required 120v power. All electrical (line voltage & low voltage) to be provided by OTHERS.
*** Trip charges included for budgetary purposes only and are subject to change upon issue of construction schedule.
*** Extra materials NOT included in above pricing.
*** Installation based on fastening shades to aluminum window system. Any change in mount substrate or location is subject to surcharge.
Motorized roller shades will require 120v power via J-box within 5' of each motor location, as well as Cat 5 data bus be run in parallel between each motor to create shade network. All electrical hardwiring, labor, materials & CONNECTIONS are to be provided by others. RWP to supply electrical controllers & wall switches, but installation, wiring & connections of these components are to be provided by the Electrical Contractor as RWP is not licensed for this type of work.
Low voltage wall switch control provided in above scope. System will be capable of individual & group shade control.
Ceiling mount wood blocking is to be provided by others at WT-1. Product quoted per spec. Plans & Wall Section details do not show a recessed pocket, but it will be required by OTHERS to hide electrical & mount hardware.
5% Extra Materials are NOT included in above quote. Window treatments are Custom ordered and 5% / 2 additional working units of each size supplied is not a cost effective or feasible approach.

## WT Description
Blinds | Roller Shades | Shutters
Custom 2" Vinyl Blinds, Standard Valance, Standard Controls (Cord Lift - Cord Tilt) | Custom Motorized Roller Shade w/ Fascia | Custom FR Rated Plantation Shutters, 3.5" Louvers, LFrame, Std Tilt, Outside Mount
Custom Ultravue 2" Faux Wood Blinds, Standard Options and Controls | Custom Single Roller Shades w/ Fascia, Manual Bead Chain Clutch Operated Control
Custom Timber Ultravue 2" Faux Wood Blinds, Std Valance w/ Magnets, Standard Controls, Inside Mount
Custom Dual Roller Shades w/ Fascia, Manual Bead Chain Clutch Operated Control Front Fabric: Fury Sheer / TBD Back Fabric: Linen Light Blackout 0% / TBD Fascia: TBD
Custom Timber Ultravue 2" Faux Wood Blinds, Std Valance w/ Magnets, Standard Controls, Inside Mount
Custom Roller Shade w/ Front/Back Fascia, Light Blocking Side/Bottom Channels, Manual Clutch Operation, Inside Mount Fabric: Avila Twilight 0% / TBD
Custom Ultravue 2" Faux Wood Blinds, Standard Options and Controls
Custom Roller Shade w/ Fascia, Light Blocking Side.Bottom Channels, Manual Clutch Operation, Inside Mount
Custom 2" Vinyl Blinds, Standard Valance, Standard Controls (Cord Lift - Cord Tilt)
Custom 1" Aluminum Horizontal Louver Blinds. Manual Cord Lift & Wand Tilt Control. | Custom Roller Shade w/ Fascia, Light Blocking Side/Bottom Channels, Manual Clutch Operation, Outside Mount
Custom Sheer Roller Shade, Manual Clutch Operation, Inside Mount
Custom Hunter Douglas Dual Roller Shades w/ Fascia, Light Blocking Side/Sill Channels, 110v Motorized Operation
Custom Dual Coupled Roller Shade, Recess Mount, RS485 Motorized Operation, Third Party Control Light Blocking Side Channels for Above Custom 10 x 5.125 Steel Pocket for Zigbee to Digital Motor Interface for aboveAbove
Custom Dual Roller Shade w/ Fascia, Side and Sill Channels Manual Bead Chain Clutch Control Custom FR Rated PVC Plantation Shutter, 2.5" Louvers, Std Tilt Control, Inside Mount
Custom Blackout Roller Shade, Battery Powered Motorized Operation, Wall Switch Control, Outside Mount
I/O AC Motorized Flexshade Roller Shades w/ Wall Clip - Closure Panel

## Products
Manufacturer | Caco | Draper | Levolor | Lutron | Mecho | Norman | Spring Window Fashions | Hunter Douglas
Sales Rep |  | Ross Rhodes | Mark Gleeson | Jason Lee | Cherie Simmons | Mark Atwood | Eric Lake
Contact Info. | debbie@cacoinc.com | rrhodes@draperinc.om | commercial.quotes@levolor.com | jnlee@lutron.com | cherie.simmons@mechoshade.com | marka@normanusa.com | eric.lake@springwindowfashions.com
| carolyn@cacoinc.com | www.draperonline.com | mark.gleeson@levolor.com | 484-264-3798 | 718-729-2020 | www.normanusa.com | contractquotes@springswindowfashions.com
| conley@cacoinc.com |  |  | www.lutron.com | www.mechoshade.cm | contractsales@normanusa.com
Acct # |  |  |  | 159778 | M82568 |  | 75143
Products |  | Manual Single Roller Shades |  | Manual Single Roller Shades | Manual Single Roller Shades | Shutters | Metal Blinds | Manual Single Roller Shades
|  | Manual Dual Roller Shades |  | Manual Dual Roller Shades | Manual Dual Roller Shades | Blinds | Vinyl Blinds | Manual Dual Roller Shades
|  | Motorized Single Roller Shades |  | Motorized Single Roller Shades | Motorized Single Roller Shades | Shades | Graber Lake Forest Faux Wood Blinds | Motorized Single Roller Shades
|  | Motorized Dual Roller Shades |  | Motorized Dual Roller Shades | Motorized Dual Roller Shades |  | Manual Roller Shades | Motorized Dual Roller Shades
[7 empty] | Dual Manual Roller Shades | 2" Faux Wood Blinds
Metal Blinds
Composite (EverWood)Blinds
Hardwood Blinds