The drapery installation schedule, referred to as "Window Treatment Installation," is as follows:

- GCI - Building 11:

  - Duration: 4 days

  - Start: Monday, February 16, 2026

  - Finish: Thursday, February 19, 2026

- GCI - Building 12:

  - Duration: 4 days

  - Start: Monday, March 9, 2026 ​

  - Finish: Thursday, March 12, 2026 ​

- GCII - Building 24:

  - Duration: 4 days

  - Start: Monday, March 23, 2026

  - Finish: Thursday, March 26, 2026

- GCII - Building 25:

  - Duration: 4 days

  - Start: Monday, March 30, 2026

  - Finish: Thursday, April 2, 2026 ​

- GCII - Building 26:

  - Duration: 4 days

  - Start: Monday, April 13, 2026

  - Finish: Thursday, April 16, 2026 ​

- GCII - Building 27:

  - Duration: 4 days

  - Start: Monday, April 20, 2026

  - Finish: Thursday, April 23, 2026 ​

- GCII - Building 28:

  - Duration: 4 days

  - Start: Monday, May 4, 2026

  - Finish: Thursday, May 7, 2026

- GCII - Building 29:

  - Duration: 4 days

  - Start: Monday, May 11, 2026

  - Finish: Thursday, May 14, 2026

This schedule spans from February 16, 2026, to May 14, 2026, with each building's installation taking 4 days. ​